## WEB (YOUTH USER)
Module | Sub Module | Step to reproduce | Description | Issue Type | URL | Test Data | Issue screenshot | Priority | Severity | Dev Status | QA Status | QA Remarks | Other's
login |  | try to login as a new user | show an login error during new user login | Functional | https://dev-platform.futurenation.gov.bd/ |  | https://prnt.sc/usK_K9IMW70O | High |  | Fixed | Done
Home | Home page | click on home button | home button does not work here. click on home button, page should takes reload. | Functional | https://dev-platform.futurenation.gov.bd/ |  | https://prnt.sc/-FAroH1_HjX5 | High |  | Processing
Home | Home page | click on logo button | logo button does not work here, it's not clickable. The logo should act as a home navigation button. | Functional | https://dev-platform.futurenation.gov.bd/ |  | https://prnt.sc/jTQDW05d6qSL | High | Medium | Fixed | Not Fixed
Create your profile |  | Create your profile | there is no restriction and alert here, check the requirements. | Functional | https://dev-platform.futurenation.gov.bd/create-profile |  | https://prnt.sc/-gwtVVGG7mAi | High | High | Fixed | Create Another issue
Create your profile | work experiences. | Create your profile | Show an unexpected error, during try to add work experiences. | Functional | https://dev-platform.futurenation.gov.bd/create-profile |  | https://prnt.sc/jvAyDVHu7FuC | High |  | Fixed | Done
Create your profile | work experiences. | Create your profile | Choose some industries is not possible | Functional | https://dev-platform.futurenation.gov.bd/create-profile |  | https://prnt.sc/LaC8BxsWR7l2 | High |  | Fixed | Done
Create your profile |  | Create your profile | Mobile number varified, but number does not show here during editing and also profile view. | Functional | https://dev-platform.futurenation.gov.bd/create-profile |  | https://prnt.sc/phfXrZqRgkZL https://prnt.sc/Cq5Xm64aWxpl | High | Critical | Fixed | Done
MY PROFILE | work experiences. | try to add work experiences. | experience add does not possible to work. | Functional | https://dev-platform.futurenation.gov.bd/my-profile |  | https://prnt.sc/FfH0504D0PHr | Urgent |  | Fixed | Done
jobs |  | click on apply button | Apply button works as a details button, button text should be changed. | UI | https://dev-platform.futurenation.gov.bd/jobs |  | https://prnt.sc/dtzee2_Qo9og | High |  | Fixed | Not Fixed
jobs |  | try to find my jobs | there is no navigation to find my jobs. how to go there?? | Logical | https://dev-platform.futurenation.gov.bd/my-jobs |  | https://prnt.sc/oF9INHtC59sj | High | Medium | Processing
jobs |  | check Application Status | Does not show proper date for Application Status | Functional | https://dev-platform.futurenation.gov.bd/my-jobs |  | https://prnt.sc/KY4x3d-mctGZ | High | Critical | Processing
jobs |  | check Application Status | Does not show proper date for jobs Application | Functional | https://dev-platform.futurenation.gov.bd/my-jobs |  | https://prnt.sc/l7agZXKB9HmB | High |  | Have Dependency
Profile Edit |  | try to check users required data. | mobile number showing issue, this required field alert issue. | Functional | https://dev-platform.futurenation.gov.bd/profile-edit |  | https://prnt.sc/xkZKd6Ombam3 https://prnt.sc/bx6Lj9YLnFrq | High | High | Fixed | Done
Job apply | Jobs | during upload cover latter | please mention the file type like PDF or something, which the user can attach here. | UI | https://dev-platform.futurenation.gov.bd/job-application/92 |  | https://prnt.sc/VEjVDQAt-wOz | Medium | Medium | Fixed | Done
All Jobs | Jobs | checking filter alignment | filter alignment issue | UI | https://dev-platform.futurenation.gov.bd/jobs |  | https://prnt.sc/gln18Era8YJT | Medium | Low | Fixed | Done
my-jobs |  | try to download offer letter | download offer letter button does not work here. | Functional | https://dev-platform.futurenation.gov.bd/my-jobs |  | https://prnt.sc/x8Wk9TnqRJmX | High | High | Fixed | Done
Home | Continue learning | Try to go Continue learning module | There is no view all courses button. should have this button | UI | https://dev-platform.futurenation.gov.bd/ |  | https://prnt.sc/adRSbJV63bCV | High | High | Fixed | Create Another issue
edit profile |  | during edit profile | alignment issue, please check the design. | UI | https://dev-platform.futurenation.gov.bd/profile-edit |  | https://prnt.sc/KOpMVtHbdM6t https://prnt.sc/g-xhWkf8ZC0t | Medium | Medium | Fixed | Done

## Moblie Application
Module | Sub Module | Steps to reproduce | Description | url | Issue Type | Issue screenshot | Priority | Severity | Expected result | Status | QA Status | QA Remarks | Dev Remarks
Sign in |  | Try to sign in using social media. | During sign in using social media account, next page always show google icon, but it should not happen. Aalways should show respective icon. |  | Functional | https://prnt.sc/t41Ri6UJSs8L | Medium | Medium |  | Done . Now clicking the signin button will take you to that page directly .i was told by previous developer to do that. so please ask them if it should be dont that way | Done
Sign in |  | Try to sign in usually. | Just click on sign in button, feature goes to the web form sign in page. but it should not happen. |  | Functional | https://prnt.sc/anrw39A-l5x2 | High | High |  | Done .will be updated in new apk. but have to consult with others about the design | Done
Home |  | try to check data lists. | Show all button does not work, sometimes show error. |  | Functional | https://prnt.sc/k47UhAdQPDjj | High | High |  | it doesnt have any functionality | Not Fixed |  | it doesnt have any functionality
Home | App Logo | during run of the application. | Logo does not show perfectly. design issue |  | UI | https://prnt.sc/6K_t9i3aO5nJ | Medium | Medium |  |  | Create Another issue
Profile | Edit Profile | during edit time | Text field issue, this text field does not allow any special character or any number. Only character is allowed here, but it should not be. When input special character or number it's work as a character switch button. |  | Functional | https://prnt.sc/RNbvirCKpFsG | High | Medium |  | Done. Need To Be Reviewed. If its working make the color green | Not Fixed | name field does not allow dot, hi-pen. location & about field does not braket and clon, semi-clon, hi-pen. | previous developer have created the app such a way that name cant have any symbols and dots.please confirm with top officials and let me know if that needs to be changed. i will change the about so that it takes all characters. but please confirm with pm and let me know.
Profile | Edit Profile | try to update profile | Click on update button show, this types of error. |  | Functional | https://prnt.sc/tBR2qc5dgM_G | High | High |  | Api is causing the problem so have to check with the api team | Done | ERROR Toast message still shows. | Api is causing the problem so have to check with the api team
Profile | Edit Profile | try to update profile | This three edit button play a same role, but it should not be. Phone number edit button should be use edit phone number, and also address edit button should be use edit only address. But phone number & mail is not editable here. |  | Functional | https://prnt.sc/-vqBDuJBZJnT https://prnt.sc/dydnKm0UZ2AT https://prnt.sc/sfmFJeDS80S6 https://prnt.sc/O83e5A_v0Nmd | Medium | Low |  | i was told phone and email cant be changes so that field is not accessible. | Done | So no need to edit button there. | by aurnab: please check again with them and let me know. i was told by my previous developer this was not editable
Profile | Edit Profile | add experience | Auto refresh does not work here, After adding any experience, initially does not show that. |  | Functional | https://prnt.sc/tP09bwtbxi_H | High | High |  | ok will check and update it | Not Fixed | it's now show error toast message without any status code | it works fine from my side. please check it in the new update file
Profile | Edit Profile | add education level | Edit button does not work here |  | UI | https://prnt.sc/_QXocbx9t8ET | High | Medium |  | Done. Need To Be Reviewed. If its working make the color green | Not Fixed
Profile | Edit Profile |  | There is no location input button, just show location icon, not any details. |  | Logical | https://prnt.sc/M6LByBZj5025 | Medium | High |  | Done. Need To Be Reviewed. If its working make the color green | Done
Profile | Edit Profile |  | education level and experience tag logo is same, it should be different. |  | UI | https://prnt.sc/z0WFjmG_x4lC | Low | Low |  | Done. Need To Be Reviewed. If its working make the color green | Done
Profile | Edit Profile | add basic skills | during edit or adding basic skills show these kinds of errors. show none status code |  | Functional | https://prnt.sc/VVHPlVXG_0GK | High | High |  | Done. Need To Be Reviewed. If its working make the color green | Done
Profile | Edit Profile | during edit profile | sometimes this error shows automatically. please check the functionalities. |  | Functional | https://prnt.sc/nkkITb1xrmGU | High | High |  | Done. Need To Be Reviewed. If its working make the color green | Done | couldn't find out this error in the new apk. maybe it's now ok, I just monitoring this issue.
Profile | Edit Profile | during edit profile | status code error |  | UI | https://prnt.sc/pl1z8Vb0kqQR | High | High |  | Done. Need To Be Reviewed. If its working make the color green | Done
Profile | Edit Profile | during edit profile | this data is not editable, so no need the edit button here. |  | Functional | https://prnt.sc/8G3qLwuc0TgS | High | Medium |  |  | Done